## Slide 1: Chapter 12 Network Analysis for Planning and Control of Maintenance Work
Instructor ; Endalk B. MSc..

## Slide 2: Scheduling
Is the process by which jobs are matched with resources and sequenced to be executed at a certain points in time.
Scheduling deals with the specific time and phasing of planned jobs together with the orders to perform the work, monitoring the work, controlling it, and reporting on job progress.
Successful planning needs a feedback from scheduling.

## Slide 3: Reliable Schedule Must Take Into Consideration
A job priority ranking reflecting the criticality of the job.
The availability of all materials needed for the work order in the plant.
The production should be in master schedule.
Realistic estimates and what is likely to happen.
Flexibility in the schedule.

## Slide 4: Maintenance Schedule Can be Prepared at Three Levels (Depend on The Time Horizon)
1. Long-range (master) schedule 2. Weekly schedule 3. Daily schedule

## Slide 5: Long-Range (master) Schedule
Covering a period of 3 months to 1 year,
Based on existing maintenance work orders (blanket work order, backlog, PM, anticipated EM).
Balancing long-term demand for maintenance work with available resources.
Spare parts and material could be identified and ordered in advance.
Subject to revision and updating to reflect changes in the plans and maintenance work

## Slide 6: Weekly Schedule
Covering 1 week.
Generated from the master schedule.
Takes into account current operations schedules and economic considerations.
Allow 10% to 15% of the workforce to be available for emergency work.
The schedule prepared for the current week and the following one in order to consider the available backlog.
The work orders scheduled in this week are sequenced based in priority.
CPM and integer programming techniques can be used to generate a schedule.

## Slide 7: Daily Schedule
Covering 1 day.
Generated from weekly schedule.
Prepared the day before.
Interrupted to perform EM.
Priorities are used to schedule the jobs.

## Slide 8: Elements of Sound Scheduling
• Written work orders that are derived from a well conceived planning process. (Work to be done, methods to be followed, crafts needed, spare parts needed, and priority). • Time standards. • Information about craft availability for each shift. • Stocks of spare parts and information on restocking

## Slide 9: Elements of Sound Scheduling
Information on the availability of special equipment and tools necessary for maintenance work.
Access to the plant production schedule and knowledge about when the facilities will be available for service without interrupting production schedule.
Well-define priorities for maintenance work.
Information about jobs already scheduled that are behind the schedule (backlog).

## Slide 10: Scheduling Procedures (Steps)
Sort backlog work orders by crafts.
Arrange orders by priority.
Compile a list of completed and carry over jobs.
Consider job duration, location, travel distance, and the possibility of combining jobs in the same area.
Schedule multi-craft jobs to start at the beginning of every shift.
Issue a daily schedule (not for shutdown maintenance).
Authorize a supervisor to make work assignments (dispatching).

## Slide 11: Maintenance Job Priority System
Priorities are established to ensure that the most critical work is scheduled first.
It is developed under coordination with operations staff.
It should be dynamic.
It must be updated periodically to reflect changes in operation and maintenance strategies.
It typically includes three to ten levels of priority.

## Slide 12: Scheduling Techniques
The objective of the scheduling techniques is to construct a time chart showing: The start and finish for each job.
The interdependencies among jobs.
The critical jobs that require special attention and effective monitoring

## Slide 13
Such Techniques are :
Modified Gantt chart
CPM
PERT
Integer and stochastic programming

## Slide 15: Network
Graphical interpretation of activities and event,
Shows dependency relationships between tasks or activities in a project,
Clearly shows tasks that must precede (precedence) or follow (succeeding) other tasks in a logical manner, and
Clear representation of plan – a powerful tool for planning and controlling project

## Slide 16: Cont..

## Slide 18: Cont.…

## Slide 19: Cont.

## Slide 20: Cont..

## Slide 21: BENEFITS OF CPM / PERT NETWORK
Consistent framework for planning, scheduling, monitoring, and controlling project.
Shows interdependence of all tasks, work packages, and work units.
Helps proper communications between departments and functions.
Determines expected project completion date.
Identifies so-called critical activities, which can delay the project completion time.

## Slide 22: Cont..
Identified activities with slacks that can be delayed for specified periods without penalty, or from which resources may be temporarily borrowed
Determines the dates on which tasks may be started or must be started if the project is to stay in schedule.
Shows which tasks must be coordinated to avoid resource or timing conflicts.
Shows which tasks may run in parallel to meet project completion date

## Slide 23: Sequence of activities

## Slide 24: Solution

## Slide 25: Cont..

## Slide 26: Solution

## Slide 27: Solution

## Slide 28: Cont.…

## Slide 29: Cont..

## Slide 31: Earliest start & earliest finish time

## Slide 32: Cont.

## Slide 33: Network with ES and EF

## Slide 34: Activity and Duration

## Slide 35: LS and LF Time

## Slide 36: Network with LS and LF time

## Slide 37: Slack or free time

## Slide 38: Example

## Slide 39: Cont..

## Slide 40
Thank you !!!